## Sheet1
Date | Milestone | Tasks | Responsible | Notes
2018-08-29 | Project Start | Form team: make introductions; inventory skill strengths and weaknesses; forumulate and document initial roles and responsibilities (to be modified as needed later). | All
2018-08-29 | Project Start | Schedule 1st team meeting - and attempt to choose recurring team meeting times that work for everyone (can be established later); establish a communications plan (ie. share emails, cell#'s, and establish how you will stay in touch) | All
2018-08-29 | Project Start | Further develop this project plan (it is part of HW1) - THINK through your time management and what you will accomplish as the weeks progress. | All
2018-09-05 | Team Meeting; 1st homework started | Have met at least once by the end of the day on 9/5; have started Homework #1 minimally | All
2018-09-12 | UML Use Case Diagram | Complete the Use Case Diagram | All
2018-09-12 | Project Plan | Complete the project plan | All
2018-09-12 | Homework #1 Due! | Have met at least twice - this is your last reminder from me in this template that you need to meet regularly outside of class - if you are not, you will not do well in this class; Have HW1 done; Have this project plan completely filled in for review and comments back so you will know if you have a good plan to get to end-game; Have your client questionnaire finalized and be prepared to interview the client. | All
| ER Diagram | Complete ER Diagram | All
| IT Requirements estimate | Complete IT estimates | All
2018-09-19 | Homework #2 Due | E-R diagrams complete with supporting documentation if explanation is required for anything you document in your diagrams. | All
All
All
2018-09-26 | Homework #3 Due | Complete mock-ups (ie. wireframes) of your user interface. | All
All
All
2018-10-03 | UML diags final; proj plan final | Final Project Plan - updated with all input from instructor Final UML Diagrams | All
All
All
2018-10-10 | Database design draft | Draft database design | All
All
All
2018-10-17 | Mid-semester peer reviews due | Complete initial (ie. first pass feedback) peer reviews | All
All
All
2018-10-24 | Draft IT requirements, including network design |  | All
All
All
2018-10-31 | Homework #4 Due | Database prototype complete | All
2018-11-07 | First Demo of Prototype | Complete project prototype first-pass demo ready | All
2018-11-14 | User Validation & Test plan finalized | Test plan for all aspects of the prototype complete User validation tests to be performed by client documented | All
2018-11-21 | Client Visit | Updates to user validation complete (as required) One key question to ask the client dcoumented | All
2018-11-28 | Draft Documentation | All documentation required for the project in Draft form | All
2018-12-05 | Paper Due - Final Documentation | All documentation required for the project in FINAL form | All
2018-12-05 | Final Peer Evaluations | Complete final peer evaluation forms and submit | All
2018-12-12 | FINAL PRESENTATION! | Git er dun! | All